## Slide 1: Project management
Viet-Trung Tran
trungtv.github.io
School of Information and Communication Technology

## Slide 2: Outline

## Slide 3: PROJECT PLANNING ACTIVITIES

## Slide 4: Key questions

## Slide 5: Accurately defining the problem
System Vision Document
  problem description
  anticipated business benefits
  system capabilities
How
  Review the business needs
  Develop a list of business benefits
  Identify the new system’s ability to support the realization of these benefits

## Slide 6: The vision document outline
Introduction
overview of the entire vision document. It includes the purpose, scope, definitions, acronyms, abbreviations, references, and an overview of the full document.
Positioning
  Business opportunity: that is addressed by this project.
  Problem statement: Summarize the problem that this project solves.
Stakeholder and user descriptions: identify and involve all stakeholders as part of the requirements-definition process
Product overview: Product perspective and Summary of capabilities
Product features
Constraints: note any design constraints, external constraints, such as operational or regulatory requirements, or other dependencies.
Quality ranges: define the quality ranges for performance, robustness, fault tolerance, usability, and similar characteristics that the feature set does not describe.
Precedence and priority
Other product requirements
Documentation Requirements

## Slide 7: PRODUCING THE PROJECT SCHEDULE
A task is the smallest piece of work that is identified and scheduled
An activity is made up of a group of related tasks or other smaller activities. Activities are also identified, named, and scheduled
For example, in the design phase
  Design the user interface (activity)
    Design the customer entry form (task)
    Design the order-entry form (task)
  Design and integrate the database, and (activity)
  Complete the application design (activity)

## Slide 8: Development of a project schedule
One of the most difficult endeavors of project planning, yet it is one of the most important
Three main steps
  Develop a work breakdown structure
  Build a schedule using a Gantt chart
  Develop resource requirements and the staffing plan

## Slide 9: Developing a work breakdown structure
The first step in building a project schedule is to identify all of the activities and tasks that need to be scheduled
Work breakdown structure (WBS) is the hierarchy of phases, activities, and tasks of a project; one method to estimate and schedule the tasks of a project
Techniques
  Top-down: Identifying major activities first and then listing internal tasks
  Bottom-up: Listing all the tasks you can think of and organizing them later
  Template: Using a standard template of tasks for projects that are fairly standard
  Analogy: Finding a similar, or analogous, project that is finished and copying its tasks

## Slide 10: WSB template for planning iteration

## Slide 11: How detailed should be the individual tasks?
There should be a way to recognize when the task is complete.
The definition of the task should be clear enough so that someone can estimate the amount of effort required to complete it.
As a general rule for software projects, the effort should take 2 to 10 working days.

## Slide 12: DEVELOPING THE SCHEDULE
A project schedule lists all project activities and tasks and the order in which they must be completed
  must identify dependencies between the tasks on the WBS
  estimate the effort that each task will require (employee effort, resource requirements and the staffing plan)

## Slide 13: IDENTIFYING PROJECT RISKS AND CONFIRMING PROJECT FEASIBILITY
Project feasibility analysis is an activity that verifies whether a project can be started and successfully completed
  Assess the risk to the project (risk management).
  Determine the organizational and cultural feasibility.
  Evaluate the technological feasibility.
  Determine the schedule feasibility.
  Assess the resource feasibility.
  Determine the economic feasibility.

## Slide 14: Risk management
Risk management is the project management area in which the team tries to identify potential trouble spots that could jeopardize the success of the project
  a careful look at the overall feasibility and at the individual risks
  done throughout the life of the project

## Slide 15: Simplified risk analysis
The best way to identify risks is simply to have a brainstorming session that include key project members and stakeholders

## Slide 16: ORGANIZATIONAL AND CULTURAL FEASIBILITY
Each company has its own culture, and any new system must be accommodated within that culture
Common organizational and cultural issues
  A current low level of computer competency
  Substantial computer phobia
  A perceived loss of control by staff or management
  Potential shifting of political and organizational power due to the new system
  Fear of change of job responsibilities
  Fear of loss of employment due to increased automation
  Reversal of long-standing work procedures
What items might prevent the effective use of the new system and the resulting loss of business benefits?

## Slide 17: TECHNOLOGICAL FEASIBILITY
What are technological requirements of the new system?
What expertise is available?
How do we mitigate these technological risks?

## Slide 18: SCHEDULE FEASIBILITY
Project scheduling is risky
  Assumptions
  Estimates
  Unknowns
  management-imposed constraints
  organizational schedule (start of season/term)
How can we avoid them?

## Slide 19: RESOURCE FEASIBILITY
The primary resource consists of team members
  Quantity and quality (skills)
  Team members may leave
Other resources
  adequate computer resources
  physical facilities
How do we avoid/minimize resource risks?

## Slide 20: ECONOMIC FEASIBILITY
Economic feasibility consists of two tests
  (1) Is the anticipated value of the benefits greater than projected costs of development? and
  (2) Does the organization have adequate cash flow to fund the project during the development period?
Common sources of increased revenue, or lowered costs
  new markets with new products, services, locations
  increased market share
  reduced staffing needs
  decreased operating costs
  decreased error rates
  reduced inventory losses
  collecting accounts more quickly

## Slide 21: Cost-benefit Analysis
Tangible costs
  personnel costs
  equipment costs
  supporting materials
  converting to new system
Intangible costs
  loss of customer good will
  staff stress and distress
  confusion with suppliers with new processes

## Slide 22: Cost-benefit Analysis
Tangible benefits
  Reduced cost
  Increased efficiency
Intangible benefits
  improved work practices
  employee morale
  ease of customer access to account details online
  up to date product information online
  increase loyalty of customers
Intangible benefits are not included in the cost/benefit analysis, but often they are the most important reason for initiating a project.

## Slide 25: Net present value, payback period, and return on investment

## Slide 26: Establish the Project Environment
Project manager must establish project parameters and the work environment
  Recording and communicating—internal and external
  Who, what, when, and how
  Work environment
    Workstations, software development tools (IDE), servers and repositories, office and meeting space, support staff
  Process and procedures followed
    Reporting and documentation, programming approach, testing, deliverables, code and version control
In other words, tailor and operationalize the methodology being used

## Slide 27: Evaluate Work Processes
Very important process for iterative projects
retrospective meeting
  a meeting to determine what was successful, and what can be improved next iteration
  done for each iteration
Monitor project progress and make corrections

## Slide 28: Thank you for your attention! Q&A