## Slide 1: Systems Analysis and Design 5th Edition Chapter 2. Project Selection and Management
Roberta Roth, Alan Dennis, and Barbara Haley Wixom

## Slide 2: Chapter 2 Outline
Project selection.
Creating the project plan.
Managing and controlling the project.

## Slide 3: INTRODUCTION
CIOs (chief information officers) are challenged to select projects that will provide highest return on the IT investments.
Project portfolio management has become a critical success factor for IT departments.
A selected system development project must undergo a thorough process of project management.
A critical success factor for project management is to start with a realistic assessment of the work and then manage the project according to the plan.

## Slide 4: PROJECT SELECTION
Systems projects today are evaluated in the context of an entire portfolio of projects.
Determination of a project’s contribution to an entire portfolio of a project reinforces the need for a feasibility study.
Portfolio management takes into consideration the different of projects that exist in an organization.

## Slide 5: (cont’d)
An approval committee must be selective about where to allocate resources as most organizations have limited funds.
If there are several potentially high-payoff projects, and they all have the same risk, then maybe only one of the projects will be selected.

## Slide 6: CREATING THE PROJECT PLAN
Project management phases consist of
- initiation
- planning
- execution
- control, and
- enclosure.

## Slide 7: Project Methodology Options
A methodology is a formalized approach to implementing the SDLC.
- Waterfall Development
- Parallel Development
- V-model (variation of the Waterfall Development)
- Rapid Application Development (RAD)
- Iterative Development
- System prototyping
- Agile Development

## Slide 8: Waterfall Development

## Slide 9: Parallel Development

## Slide 10: V-model

## Slide 11: Rapid Application Development: Iterative Development

## Slide 12: Rapid Application Development: System Prototyping

## Slide 13: (cont’d)
Throwaway prototyping

## Slide 14: Agile Development
A group of programming-centric methodologies that focus on streamlining the SDLC.
Includes face-to-face communication
Extreme programming – emphasizes customer satisfaction and teamwork.

## Slide 15: Extreme Programming

## Slide 16: Selecting the Appropriate Development Methodology

## Slide 17: (cont’d)
Important factors to consider in selecting the development methodology
- Clarity of User Requirements
- Familiarity with Technology
- System Complexity
- System Reliability
- Short Time Schedules
- Schedule Visibility

## Slide 18: Estimating the Project Time Frame
1. Estimating Project Time Using Industry Standards
2. Function point approach (Appendix 2A)

## Slide 19: Developing the Work Plan
Identify Tasks

## Slide 20: (cont’d)
Work Breakdown Structure

## Slide 21: (cont’d)
The project work plan

## Slide 22: STAFFING THE PROJECT
Staffing Plan
- Staffing levels will change over a project’s lifetime
- Adding staff may add more overhead than additional labor
- Using teams of 8-10 reporting in a hierarchical structure can reduce complexity

## Slide 23: (cont’d)
Reporting structure

## Slide 24: (cont’d)
The staffing plan describes the kinds of people working on the project
The project charter describes the project’s objectives and rules
A functional lead manages a group of analysts
A technical lead oversees progress of programmers and technical staff members

## Slide 25: Motivation
Use monetary rewards cautiously
Use intrinsic rewards
  Recognition
  Achievement
  The work itself
  Responsibility
  Advancement
  Chance to learn new skills

## Slide 26: Handling Conflict
Clearly define plans for the project.
Recognize project importance to organization.
Project charter listing norms and ground rules.
Develop schedule commitments ahead of time.
Forecast other priorities and their possible impact on the project.

## Slide 27: Coordinating Project Activities
CASE (computer-aided software engineering) tools – A category of software that automate all or part of the development process.
- Upper CASE
- Lower CASE
- Integrated CASE

## Slide 28: (cont’d)
Standards
  Formal rules for naming files
  Forms indicating goals reached
  Programming guidelines
Documentation
  Project binder
  Table of contents
  Continual updating

## Slide 29: MANAGING AND CONTROLLING THE PROJECT
The science (or art) of project management is in making trade-offs among three important concepts:
- the size of the system,
- the time to complete the project, and
- the cost of the project.

## Slide 30: (cont’d)
Tools for project management – Example of Gantt Chart

## Slide 31: Refining Estimates

## Slide 32: Managing Scope
Scope creep – the most common reason for schedule and cost overruns occurs after the project is underway.
The project manager should allow only absolutely necessary requirements to be added after the project begins.

## Slide 33: Timeboxing
Set a fixed deadline for a project
Reduce functionality, if necessary
Don’t get hung up on the final “finishing touches”

## Slide 34: Timeboxing steps

## Slide 35: Managing Risk
Risk assessment
Actions to reduce risk
Revised assessment

## Slide 36: SUMMARY
The project selection process takes into account all of the projects in the organization, using project portfolio management.
The project plan defines the tasks, task time estimates, and other information.
A project requires staffing and coordinating project activities.
Managing and controlling the project include timeboxing and risk assessment.

## Slide 37: Copyright 2011 John Wiley & Sons, Inc.
All rights reserved. Reproduction or translation of this work beyond that permitted in Section 117 of the 1976 United States Copyright Act without the express written permission of the copyright owner is unlawful. Request for further information should be addressed to the Permissions Department, John Wiley & Sons, Inc. The purchaser may make back-up copies for his/her own use only and not for redistribution or resale. The Publisher assumes no responsibility for errors, omissions, or damages, caused by the use of these programs or from the use of the information contained herein.